## PM & Common
<Project_Name>
Project Management and Common Systems | Month: | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 |  |  |  |  | Proj. dur. (Mons): | 37
|  | 2022-07-01 | 2022-08-01 | 2022-09-01 | 2022-10-01 | 2022-11-01 | 2022-12-01 | 2023-01-01 | 2023-02-01 | 2023-03-01 | 2023-04-01 | 2023-05-01 | 2023-06-01 | 2023-07-01 | 2023-08-01 | 2023-09-01 | 2023-10-01 | 2023-11-01 | 2023-12-01 | 2024-01-01 | 2024-02-01 | 2024-03-01 | 2024-04-01 | 2024-05-01 | 2024-06-01 | 2024-07-01 | 2024-08-01 | 2024-09-01 | 2024-10-01 | 2024-11-01 | 2024-12-01 | 2025-01-01 | 2025-02-01 | 2025-03-01 | 2025-04-01 | May-25 | 2025-06-01 | 2025-07-01 | Comments | Sub total hours | Hours Total: | Hour Price (EUR): | Total cost (EUR): | Loading Avg.
Project Timeline |  | Basic Design |  |  |  |  | Detailed design |  |  |  | Manufacturing | [6 empty] | FAT | Deliv. |  | Installation |  |  | HAT |  |  | Sailaway |  |  |  | Offshore SAT |  |  |  | Hold | As Built + Proj. Closure
Basic Design |  | Basic Design
Detailed Design (Primary Parts) | [6 empty] | Detailed design
Manufacturing (Primary Parts) | [10 empty] | Manufacturing
FAT Testing (Primary Parts) | [17 empty] | FAT
Detailed Design (Secondary Systems) | [6 empty] | Detailed design
Manufacturing (Secondary Parts) | [13 empty] | Manufacturing
FAT Testing (Secondary Parts) | [16 empty] | FAT
Delivery to Site | [18 empty] | Deliv.
Installation at Yard | [20 empty] | Installation
HAT | [23 empty] | HAT
OSAT | [30 empty] | Offshore SAT
Project Closure | [35 empty] | As Built + Proj. Closure
General PM |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 114.094 | 0 | 0%
Project startup |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
Contract Reading
Project Plan
Time Schedule
WBS plan
Risk&Opportunity Analysis
Document Structure (Sharepoint + Tekdok)
Requirement Register
Stakeholder Analysis
Procurement Plan
Project Kick off Meeting Prep
Project Kick off Meeting with Team
Project Quality Plan
Project group meetings |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
Prep for meetings
Meetings
Project reviews (Milestones) | [39 empty] | 0
Project follow-up |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
Economy Followup
Followup on PM processes
Project closing and evaluation |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
Project closure Report
Handover meeting to Service
Financial Closing
Archiving Documentation
Contract closing with Customer
Monthly progress report to customer | [39 empty] | 0
Project follow-up with customer | [39 empty] | 0
External meetings | [39 empty] | 0
TPM, Mechanical (GIS, TR, SHR, EAT) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 110.7383 | 0 | 0%
Project startup |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
Contract Reading
Risk&Opportunity Analysis
Document Structure (Sharepoint + Tekdok)
Requirement Register
Project Kick off Meeting with Team
Project group meetings |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
Meetings |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project closing and evaluation |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
Project closure Report
Handover meeting to Service
Archiving Documentation
TR & SHR Coordination |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
Coordination/alignment/project meetings
Basic Design Preparation
Detailed Design Preparation
Logistics coordination & Factory
Site Coordination
Hand Over Activities
Coordinating EAT Delivery |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
Basic Design Preparation
Detailed Design Preparation
Logistics coordination & Factory
Site Coordination
Hand Over Activities
Activities 66kV GIS |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
Primary Parts
Secondary Parts
Fabrication
Transportation
Control Cabling
Installation & commissioning
Back office I&C Support
Activities 275kV GIS |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
Primary Parts
Secondary Parts
Fabrication
Transportation
Control Cabling
Installation & commissioning
Back office I&C Support
TPM, Electrical (Interfaces, Secondary Systems & Control Cable Eng.) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 110.7383 | 0 | 0%
Project startup |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
Contract Reading
Risk&Opportunity Analysis
Document Structure (Sharepoint + Tekdok)
Requirement Register
Project Kick off Meeting with Team
Project group meetings |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
Meetings |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project closing and evaluation |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
Project closure Report
Handover meeting to Service
Archiving Documentation
Interface Management Tasks |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
Interface Mapping
Alignment of Interfaces with factories & suppliers
Workshops on Platform Design
Workshops for internal Interfaces
Site Interface Coordination/Support
Cable Engineering |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
Alignment of cable interfaces
Alignment of cable overview/tool
Alignment of cable installation documentation
Alignment of cable schedules after site works
Coordination of cable works on site
Lead Engineer, Control Cables |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 60 | 0 | 0%
Creation of Cable Overview/Cable Tool | [39 empty] | 0
Preparation of Cable Documentation for Installation | [39 empty] | 0
Preparation of Cable Schedules after site works | [39 empty] | 0
As Built Documentation | [39 empty] | 0
Lead Engineer, ICMS |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 107.3826 | 0 | 0%
Preparation of ICMS Specification
Preparation of ICMS RFQ Package
Facilitation of RFQ Process /w Procurement
Alignments with ICMS Supplier
Handling Deliverables & Interfaces through project execution
FAT Test of Equipment + followup on snags
Delivery of Equipment
Support during site works
As Built Documentation
Lead Engineer, CT/VT calculations |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 60 | 0 | 0%
Clarifications with PCM Team & Protection Studies
Calculations of CT & VT Data
Alignments with GIS team
Alignments with TR, SHR, EAT suppliers on CT's
Project Controller/CPM |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 97.3154 | 0 | 0%
Creating WBS structure
Setting up project in SAP / Closing
Handling invoices + PO's
General Followup on project
Prep for Economy meetings
Economy followup meetings
Project meetings
SCM prep + meeting
Quality Manager |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 114.094 | 0 | 0%
Planning QA activities
Preparation of PQP
Support for preparation of ITP's
Inspections site
Monthly reporting
Project Meetings
PM assessments
QC
EHS Manager |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 114.094 | 0 | 0%
Preparation of EHS Plans
Monthly reporting
RA/MS
Site Follow up / meetings
Site Inspections
HAZID WS
COSHH
HSF documentation
Purchaser / Strategic Procurement |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 77.1812 | 0 | 0%
Creating Purchase Plan
Placing PO's
Assistance with suppliers
ICMS Tender
Participation in Project Meetings
Secondary Engineer Lead |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 107.3826 | 0 | 0%
Activities 66kV GIS + Protection Panels |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
Secondary Parts
FAT & SAT
As Built
Activities 275kV GIS + Protection Panels |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
Secondary Parts
FAT & SAT
As Built
Secondary Engineer |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 60 | 0 | 0%
Activities 66kV GIS + Protection Panels |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
Secondary Parts
FAT & SAT
As Built
Activities 275kV GIS + Protection Panels |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
Secondary Parts
FAT & SAT
As Built
DK Document Controller |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 87.2483 | 0 | 0%
Setting up document structure
Final As Built documentation
General ongoing documentation followup
Activities 66kV GIS |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Primary Parts
Secondary Parts
Control Cabling
Installation & commissioning
Offshore Commissioning
Activities 275kV GIS |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Primary Parts
Secondary Parts
Control Cabling
Installation & commissioning
Offshore Commissioning
Activities Transformers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Design Documentation
FAT & Protocols
Site Documentation
As Built Documentation
Activities Shunt Reactors |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Design Documentation
FAT & Protocols
Site Documentation
As Built Documentation
Activities Earthing Auxiliary Transformers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Design Documentation
FAT & Protocols
Site Documentation
As Built Documentation
Activities ICMS |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Design Documentation
FAT & Protocols
Site Documentation
As Built Documentation
Activities Control Cabling |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Design Documentation
Site Documentation
As Built Documentation
Contract Manager | [40 empty] | 0 | 114.094 | 0 | 0%
[40 empty] | Total All Project: |  |  | 0
Site Manager |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 110.7383 | 0 | 0%
Site HSE Manager |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 110.7383 | 0 | 0%
Site Commissioning Manager |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 110.7383 | 0 | 0%
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Total Site Cost: |  |  |  | 0
|  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
DK Project Travel Cost | [42 empty] | 0 | See tab "DK Project Travel Cost"
Total All: | [38 empty] | Total All: |  | 0 |  | 0
Total All (w/o Site): | [38 empty] | Total All (w/o Site): |  | 0 |  | 0

## Workload Histogram
Project Duration: | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37
Month: | 2022-07-01 | 2022-08-01 | 2022-09-01 | 2022-10-01 | 2022-11-01 | 2022-12-01 | 2023-01-01 | 2023-02-01 | 2023-03-01 | 2023-04-01 | 2023-05-01 | 2023-06-01 | 2023-07-01 | 2023-08-01 | 2023-09-01 | 2023-10-01 | 2023-11-01 | 2023-12-01 | 2024-01-01 | 2024-02-01 | 2024-03-01 | 2024-04-01 | 2024-05-01 | 2024-06-01 | 2024-07-01 | 2024-08-01 | 2024-09-01 | 2024-10-01 | 2024-11-01 | 2024-12-01 | 2025-01-01 | 2025-02-01 | 2025-03-01 | 2025-04-01 | May-25 | 2025-06-01 | 2025-07-01
| Basic Design |  |  |  |  | Detailed design |  |  |  | Manufacturing | [6 empty] | FAT | Deliv. |  | Installation |  |  | HAT |  |  | Sailaway |  |  |  | Offshore SAT |  |  |  | Hold | As Built + Proj. Closure
Project Role: | [37 empty] | Project Average:
General PM | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
TPM, Mechanical (GIS, TR, SHR, EAT) | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
TPM, Electrical (Interfaces, Secondary Systems & Control Cable Eng.) | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Lead Engineer, Control Cables | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Lead Engineer, ICMS | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Lead Engineer, CT/VT calculations | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
DK CPM (GIS + SCS&P + Overall) | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
DK QMiP | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
DK EHS | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
DK Purchaser / Strategic Procurement | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Secondary Engineer Lead | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Secondary Engineer (Engineering Assistance) | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
DK Document Controller | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Contract Manager | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
EA1N Site Manager | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
EA1N Site HSE Manager | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
EA1N Site Commissioning Manager | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%

## DK Project Travel Cost
Activity: | Travels Ext: | Travels DK: | Days:
PM Travel
Project Meetings
TPM Mechanical Travel
Transformer & SHR FAT
EAT FAT
GIS 66kV FAT
GIS 275kV FAT
TR & SHR Site
GIS 66kV Site
GIS 275kV Site
TPM Electrical & Interface Travel
Site Interfaces
Site Cables
QEHSMiP Travel
Site Inspections
Lead Engineer ICMS Travel
ICMS FAT
ICMS Site
Secondary Engineer Travel
66kV GIS FAT
275kV GIS FAT
66kV GIS SAT
275kV GIS SAT
Totals: | 0 | 0 | 0
Cost pr. Travel Abroad: | Price: | Amount: | total:
Flight Tickets (round trip) | 750 | 0 | 0
Cost pr. Travel DK: | Price: | Amount: | total:
Car travel 300km | 348.9933 | 0 | 0
Cost pr. Day:
Hotel | 130 | 0 | 0
Rental Car | 0 | 0 | 0
Allowance/Meals | 75 | 0 | 0
Total All: |  |  | 0

## GIS TPM+Eng Overview
66kV GIS
Project type |  | Insert: | Variable
Project duration in months: |  | 38 | x
Project duration of site activities in Weeks: |  | 16 | z
Amount of switchgears: |  | 4 | y
Manufacturing duration in months: |  | 9 | u
If Onshore Project (Insert 1) |  |  | v
Total amount of typicals all switchgears |  | 6 | w
Total amount of Bay's all switchgears |  | 48 | q
Manpower for Installation |  | 0 | o
LCC (Free Standing/Integrated) |  | 48 | a
LCC Typicals |  | 6 | b
Protection Panel (Free Standing) |  | 48 | d
Protection Typicals |  | 6 | e
Combined Panel (Free Standing/Integrated) |  | 0 | f
Combined Panel Typicals |  | 0 | g
SCADA Panel |  | 0 | h
SCADA Panel Typicals |  | 0 | i
US/UK Requirements | x1,3 | 1.3 | j
Pre-FAT Required | x2 | 2 | k
Engineering Hours |  | 0
Hours per month: |  | 178.8421
Total All: |  | 6796
Total TPM Hours: |  | 1730.4
Total Engineer Hours: |  | 4369.6
Total Doc. Controller Hours: |  | 696
220kV GIS
Project type |  | Insert: | Variable
Project duration in months: |  | 38 | xx
Project duration of site activities in Weeks: |  | 6 | zz
Amount of switchgears: |  | 4 | yy
Manufacturing duration in months: |  | 9 | uu
If Onshore Project (Insert 1) |  |  | vv
Total amount of typicals all switchgears |  | 1 | ww
Total amount of Bay's all switchgears |  | 4 | qq
Manpower for Installation |  | 0 | oo
LCC (Free Standing/Integrated) |  | 4 | aa
LCC Typicals |  | 2 | bb
Protection Panel (Free Standing) |  | 4 | dd
Protection Typicals |  | 2 | ee
Combined Panel (Free Standing/Integrated) |  | 0 | ff
Combined Panel Typicals |  | 0 | gg
SCADA Panel |  | 0 | hh
SCADA Panel Typicals |  | 0 | ii
US/UK Requirements | x1,3 | 1.3 | jj
Pre-FAT Required | x2 | 2 | kk
Engineering Hours |  | 0
Hours per month: |  | 89.5789
Total All: |  | 3404
Total TPM Hours: |  | 1294.4
Total Engineer Hours: |  | 1413.6
Total Doc. Controller Hours: |  | 696

## 66kV GIS TPM+Eng
Engineering |  | Hours: | Total Hours: | TPM | Engineer | Doc Controller | Comments
TT WBD Primary parts Before design freeze | Give input to ITP | 1 | 4 | 4 |  |  | Split between 66kV & 155kV
| Clarification of Single Line Diagram | 1 | 4 | 4
| Clarification of Layout and sections | 1 | 4 | 4
| Clarification of Constructional data | 1 | 4 | 4
| Clarification of 3D model | 1 | 4 | 4
| Clarification of SKID solution | 0 | 0 | 0 |  |  | Not Relevant
| Clarification of accessibility to devices | 2 | 8 | 8 |  |  | Part of SAG Scope, only coordination required
| Clarification of Earthing plan | 2 | 8 | 8 |  |  | Only checks
| Clarification of device drawings for HV devices | 2 | 10.4 | 10.4
| Clarification of electrical load list for devices | 2 | 8 | 8
| Generation of Technical Description | 0 | 0 | 0 |  |  | Not required, SAG provides
| Generation of design report acc to MTS | 0 | 0 | 0 |  |  | Not required, SAG provides
| Design review meeting | 3 | 12 | 12 |  |  | Design Review meeting with customer
| Document controlling | 8 | 32 |  |  | 32
After design freeze | Clarification of detailed steel drawings for manufact. | 2 | 8 | 8 |  |  | Part of SAG Scope, only coordination required
| Clarification of detailed gangway drawings for manufact. | 2 | 8 | 8 |  |  | Part of SAG Scope, only coordination required
| Clarification of detailed earthing for manufact. | 0 | 0 | 0 |  |  | Part of SAG Scope
| Clarification of CB model, capacitive model, ferro ressonn | 0 | 0 | 0 |  |  | Not required
| Clarification of FAT parameters - FAT plan | 4 | 16 | 16
| Clarification of SAT protocols | 12 | 48 | 48
| Clarification of outstanding points from FAT | 2 | 8 | 8
| Planning of logistics to merging point for primary parts | 0 | 0 | 0 |  |  | Merging point not relevant
| Clarification of labeling | 8 | 62.4 | 62.4
| Follow up on delivery (NCR, missing parts etc.) | 12 | 48 | 48
| Clarification of As built for primary parts | 8 | 32 | 32
| Document controling | 35 | 140 |  |  | 140
Activities for fabrication | FAT Berlin | 16 | 64 | 64 |  |  | 1 day travel + 1 day FAT
Activities for transportation | Planning of logistics from factory/merging point to site | 8 | 32 | 32
| Planning of logistic of direct supplies from factory to merging point | 0 | 0 | 0 |  |  | Merging point not relevant
| Clarification of storage conditions at site | 2 | 8 | 8
TT WBS Secondary parts Before design freeze | Review of secondary device drawings | 8 | 32 |  | 32
| Creation of load list for devices | 4 | 16 |  | 16
After design freeze | Clarification of input from Employers requirements | 2 | 10.4 |  | 10.4
| Creation of interlocking concept | 16 | 83.2 |  | 83.2
| Creation of basic design document for Panels | 8 | 41.6 |  | 41.6
| Creation of wiring diagrams common drawings | 16 | 83.2 |  | 83.2
| Creation of Wiring diagrams LCC Typical x / Per typical | 35 | 546 |  | 546
| Creation of Wiring diagrams LCC Typical x / per swg ( meetering typpical) | 17 | 88.4 |  | 88.4
| Integration of Protection Devices in Panels | 6 | 288 |  | 288
| Integration of BCU in Panels | 6 | 288 |  | 288
| Design review meeting | 4 | 20.8 | 20.8 | 20.8 |  | Design Review meeting with customer TPM + ENG
| Creation of all LCC for all panels | 6 | 576 |  | 576
| Submittal of documentation for manufact. | 4 | 48 |  | 48
| Submittal of documentation for test boxes | 6 | 72 |  | 72
| Clarification of FAT parameters - FAT plan | 16 | 128 |  | 128
| Preparation of FAT documentation (ELCAD/Print out) | 1 | 192 |  | 192
| Clarification of SAT protocols | 16 | 64 |  | 64
| Clarification of outstanding points FAT | 8 | 64 |  | 64
| Preparation of SAT documentation (ELCAD/print out) | 24 | 96 |  | 96
| Planning of logistics to merging point for secondary parts | 0 | 0 | 0 |  |  | Merging point not relevant
| Follow up on delivery (NCR, missing parts etc.) | 8 | 32 | 32
| Creation of As built for secondary parts | 24 | 96 |  | 96
| Document controling | 48 | 384 |  |  | 384
Activities for fabrication | Execution of FAT Poland (LCC functional test) | 8 | 1536 |  | 1536 |  | Part of Calculation
Activities for transportation | Planning of logistics from factory/merging point to site | 2 | 8 | 8
| Planning of logistic of direct supplies from factory to merging point | 1 | 4 | 4
| Clarification of storage conditions at site | 1 | 4 | 4
Control cables Before design freeze | Clarification of voltage drops and general cable specification | 4 | 20.8 | 20.8
| Document controlling | 1 | 4 |  |  | 4
After design freeze | Generation of cable lists for typical x / hours per typical | 8 | 96 | 96
After design freeze | Generation of cable lists for typical x / hours per SWG | 4 | 16 | 16
| Clarification Harting design and glands | 4 | 16 | 16
| Submittal of documentation for manufact. HELU | 4 | 16 | 16
| Submittal of documentation for manufact. ETP | 4 | 16 | 16
| Follow up on delivery (NCR, missing parts etc.) | 4 | 16 | 16
| Clarification as built for control cables | 2 | 8 | 8
| Document controlling | 8 | 32 |  |  | 32
Activities for transportation | Planning of logistics from factory/merging point to site | 2 | 8 | 8
| Planning of logistic of direct supplies from factory to merging point | 0 | 0 | 0 |  |  | Merging point not relevant
| Clarification of storage conditions at site | 0 | 0 | 0
Installation and commisioning Activity for instalation | Clarification of ressources (reservation in HQ) | 4 | 16 | 16
| Evaluation of installation concept - give input to design group | 4 | 16 | 16
| Give input to HSE plan and RAMS in regards to method statements | 16 | 64 | 64
| Clarification preconditions for site work | 4 | 16 | 16
| Create detailed installation time schedule | 4 | 16 | 16
| Planning of logistics of tool container | 2 | 8 | 8
| Site visits from back office | 16 | 64 | 64
| Clarification filled out installation protocols for as built | 8 | 32 | 32
| Document controlling | 8 | 32 |  |  | 32
Activity for SAT & commisionning | Clarification of ressources (reservation in HQ) | 4 | 16 | 16
| Evaluation of commisioning concept - give input to design group | 4 | 16 | 16
| Give input to HSE plan and RAMS in regards to method statements | 8 | 32 | 32
| Clarification preconditions for site work | 4 | 16 | 16
| Create detailed commisioning time schedule | 4 | 16 | 16
| Planning of logistics of commisioning tools | 2 | 8 | 8
| Site visits from back office | 12 | 48 | 48
| Back office comm | 16 | 64 | 64
| Clarification filled out SAT protocols for as built | 12 | 48 | 48
| Document controlling | 8 | 32 |  |  | 32
Order of accesorries for GIS installation Activity for instalation | Handling chemicals from Berlin | 4 | 16 | 16
| Handling order SF6 gas | 0 | 0 | 0 |  |  | Part of SAG order
| Clarification of Safety Data sheets - give input to HSE | 4 | 16 | 16
| Planning of logitics of Chemicals and SF6 gas to site | 2 | 8 | 8
| Document controlling | 10 | 40 |  |  | 40
Order of manpower for installation Activity for instalation | Give technical input to tender material | 0 | 0 | 0 |  |  | Not relevant, Customer provision
| Prepare site documentation for manpower company | 0 | 0 | 0 |  |  | Not relevant, Customer provision
| Follow up on progress on site (2h/week) | 0 | 0 | 0 |  |  | Not relevant, Customer provision
| Collection of installation protocols filled out by manpower company | 0 | 0 | 0 |  |  | Not relevant, Customer provision
| Document controlling | 0 | 0 |  |  | 0
Order of lifting equipment and scaffolding Activity for instalation | Clarify type of cranes needed | 0 | 0 | 0
| Clarify type of scaffolding needed | 0 | 0 | 0
| Clarification of lifting plans | 0 | 0 | 0
| Submit orders | 0 | 0 | 0
| Document controlling | 0 | 0 |  |  | 0
IDB - BCU After design freeze | Clarification of signal list (to be filled out) | 0 | 0 |  | 0
| Clarification logics and LEDs (to be filled out) | 0 | 0 |  | 0
| Paramatrisation of DIGSI (to be filled out) | 0 | 0 |  | 0
| As built documentation | 0 | 0 |  | 0
Activities for fabrication | Execution of FAT Poland (BCU/functional test) | 0 | 0 |  | 0
Activity for SAT & commisionning | Execution of SAT UK site (assistance to the SIE AG comm engineer) Hours per Bay | 0 | 0 |  | 0
Activity for SAT & commisionning | Execution of SAT UK site (assistance to the SIE AG comm engineer) hours per SWG | 0 | 0 |  | 0
| Back office support for inst. | 8 | 512 | 512
Preparation of the switchgear for sail-away | Back office | 0 | 0 | 0
Filling of SF6 offshore, testing and final commissioning | Back office | 0 | 0 | 0
Totals: |  |  |  | 1730.4 | 4369.6 | 696
TPM: | Primary Parts - Basic design: | 66.4
| Primary Parts - Detailed design: | 230.4
| Primary Parts - Manufact. & FAT: | 64
| Primary Parts - Delivery: | 40
| Sec Parts - Detailed Design: | 20.8
| Sec Parts - Delivery: | 48
| Cables - Basic Design: | 20.8
| Cables - Detailed Design: | 184
| Cables - Delivery: | 8
| I&C - Installation: | 272
| I&C - SAT: | 264
| I&C - Back office support: | 512
Sec. Eng: | Sec Parts - Basic design: | 1497.6
| Sec Parts - Detailed Design: | 1240
| Sec Parts - FAT | 1536
| Sec Parts - As Built | 96
Doc. Controller: | Primary Parts - Basic design: | 32
| Primary Parts - Detailed design: | 140
| Sec Parts - Detailed Design: | 384
| Cables - Basic Design: | 4
| Cables - Detailed Design: | 32
| I&C - Installation: | 72
| I&C - SAT: | 32

## 275kV GIS TPM+Eng
Engineering |  | Hours: | Total Hours: | TPM | Engineer | Doc Controller | Comments
TT WBD Primary parts Before design freeze | Give input to ITP | 1 | 4 | 4 |  |  | Split between 66kV & 155kV
| Clarification of Single Line Diagram | 1 | 4 | 4
| Clarification of Layout and sections | 1 | 4 | 4
| Clarification of Constructional data | 1 | 4 | 4
| Clarification of 3D model | 1 | 4 | 4
| Clarification of SKID solution | 0 | 0 | 0 |  |  | Not Relevant
| Clarification of accessibility to devices | 2 | 8 | 8 |  |  | Part of SAG Scope, only coordination required
| Clarification of Earthing plan | 2 | 8 | 8 |  |  | Only checks
| Clarification of device drawings for HV devices | 2 | 10.4 | 10.4
| Clarification of electrical load list for devices | 2 | 8 | 8
| Generation of Technical Description | 0 | 0 | 0 |  |  | Not required, SAG provides
| Generation of design report acc to MTS | 0 | 0 | 0 |  |  | Not required, SAG provides
| Design review meeting | 3 | 12 | 12 |  |  | Design Review meeting with customer
| Document controlling | 8 | 32 |  |  | 32
After design freeze | Clarification of detailed steel drawings for manufact. | 2 | 8 | 8 |  |  | Part of SAG Scope, only coordination required
| Clarification of detailed gangway drawings for manufact. | 2 | 8 | 8 |  |  | Part of SAG Scope, only coordination required
| Clarification of detailed earthing for manufact. | 0 | 0 | 0 |  |  | Part of SAG Scope, only coordination required
| Clarification of CB model, capacitive model, ferro ressonn | 0 | 0 | 0 |  |  | Not required
| Clarification of FAT parameters - FAT plan | 4 | 16 | 16
| Clarification of SAT protocols | 12 | 48 | 48
| Clarification of outstanding points from FAT | 2 | 8 | 8
| Planning of logistics to merging point for primary parts | 0 | 0 | 0 |  |  | Merging point not relevant
| Clarification of labeling | 8 | 10.4 | 10.4
| Follow up on delivery (NCR, missing parts etc.) | 12 | 48 | 48
| Clarification of As built for primary parts | 8 | 32 | 32
| Document controling | 35 | 140 |  |  | 140
Activities for fabrication | FAT Berlin | 16 | 64 | 64 |  |  | 1 day travel + 1 day FAT
Activities for transportation | Planning of logistics from factory/merging point to site | 8 | 32 | 32
| Planning of logistic of direct supplies from factory to merging point | 0 | 0 | 0 |  |  | Merging point not relevant
| Clarification of storage conditions at site | 2 | 8 | 8 |  |  | Handled in 66kV
TT WBS Secondary parts Before design freeze | Review of secondary device drawings | 8 | 32 |  | 32
| Creation of load list for devices | 4 | 16 |  | 16
After design freeze | Clarification of input from Employers requirements | 2 | 10.4 |  | 10.4
| Creation of interlocking concept | 16 | 83.2 |  | 83.2
| Creation of basic design document LCC & BCU | 8 | 41.6 |  | 41.6
| Creation of wiring diagrams common drawings | 16 | 83.2 |  | 83.2
| Creation of Wiring diagrams LCC Typical x / Per typical | 35 | 182 |  | 182
| Creation of Wiring diagrams LCC Typical x / per swg ( meetering typpical) | 17 | 88.4 |  | 88.4
| Integration of Protection Devices in Panels | 6 | 24 |  | 24
| Integration of BCU in Panel | 6 | 24 |  | 24
| Design review meeting | 4 | 20.8 | 20.8 | 20.8 |  | Design Review meeting with customer TPM + ENG
| Creation of all LCC for all panels | 6 | 48 |  | 48
| Submittal of documentation for manufact. | 4 | 16 |  | 16
| Submittal of documentation for test boxes | 6 | 24 |  | 24
| Clarification of FAT parameters - FAT plan | 16 | 128 |  | 128
| Preparation of FAT documentation (ELCAD/Print out) | 1 | 16 |  | 16
| Clarification of SAT protocols | 16 | 64 |  | 64
| Clarification of outstanding points FAT | 8 | 64 |  | 64
| Preparation of SAT documentation (ELCAD/print out) | 24 | 96 |  | 96
| Planning of logistics to merging point for secondary parts | 0 | 0 | 0 |  |  | Merging point not relevant
| Follow up on delivery (NCR, missing parts etc.) | 8 | 32 | 32
| Creation of As built for secondary parts | 24 | 96 |  | 96
| Document controling | 48 | 384 |  |  | 384
Activities for fabrication | Execution of FAT Poland (LCC functional test) | 16 | 256 |  | 256 |  | Part of Calculation
Activities for transportation | Planning of logistics from factory/merging point to site | 2 | 8 | 8
| Planning of logistic of direct supplies from factory to merging point | 1 | 4 | 4
| Clarification of storage conditions at site | 1 | 4 | 4 |  |  | Included in 66kV
Control cables Before design freeze | Clarification of voltage drops and general cable specification | 4 | 20.8 | 20.8
| Document controlling | 1 | 4 |  |  | 4
After design freeze | Generation of cable lists for typical x / hours per typical | 8 | 32 | 32
After design freeze | Generation of cable lists for typical x / hours per SWG | 4 | 16 | 16
| Clarification Harting design and glands | 4 | 16 | 16
| Submittal of documentation for manufact. HELU | 4 | 16 | 16
| Submittal of documentation for manufact. ETP | 4 | 16 | 16
| Follow up on delivery (NCR, missing parts etc.) | 4 | 16 | 16
| Clarification as built for control cables | 2 | 8 | 8
| Document controlling | 8 | 32 |  |  | 32
Activities for transportation | Planning of logistics from factory/merging point to site | 2 | 8 | 8
| Planning of logistic of direct supplies from factory to merging point | 0 | 0 | 0 |  |  | Merging point not relevant
| Clarification of storage conditions at site | 0 | 0 | 0
Installation and commisioning Activity for instalation | Clarification of ressources (reservation in HQ) | 4 | 16 | 16 |  |  | Performed in 66kV GIS
| Evaluation of installation concept - give input to design group | 4 | 16 | 16
| Give input to HSE plan and RAMS in regards to method statements | 16 | 64 | 64
| Clarification preconditions for site work | 4 | 16 | 16 |  |  | Performed in 66kV GIS
| Create detailed installation time schedule | 4 | 16 | 16 |  |  | Input to 66kV GIS schedule
| Planning of logistics of tool container | 2 | 8 | 8 |  |  | Included in 66kV GIS
| Site visits from back office | 16 | 64 | 64
| Clarification filled out installation protocols for as built | 8 | 32 | 32
| Document controlling | 8 | 32 |  |  | 32
Activity for SAT & commisionning | Clarification of ressources (reservation in HQ) | 4 | 16 | 16
| Evaluation of commisioning concept - give input to design group | 4 | 16 | 16
| Give input to HSE plan and RAMS in regards to method statements | 8 | 32 | 32
| Clarification preconditions for site work | 4 | 16 | 16 |  |  | Included in 66kV GIS
| Create detailed commisioning time schedule | 4 | 16 | 16
| Planning of logistics of commisioning tools | 2 | 8 | 8
| Site visits from back office | 12 | 48 | 48
| Back office comm | 16 | 64 | 64
| Clarification filled out SAT protocols for as built | 12 | 48 | 48
| Document controlling | 8 | 32 |  |  | 32
Order of accesorries for GIS installation Activity for instalation | Handling chemicals from Berlin | 4 | 16 | 16
| Handling order SF6 gas | 0 | 0 | 0 |  |  | Part of SAG scope
| Clarification of Safety Data sheets - give input to HSE | 4 | 16 | 16
| Planning of logitics of Chemicals and SF6 gas to site | 2 | 8 | 8
| Document controlling | 10 | 40 |  |  | 40
Order of manpower for installation Activity for instalation | Give technical input to tender material | 0 | 0 | 0 |  |  | Not relevant, Customer provision
| Prepare site documentation for manpower company | 0 | 0 | 0 |  |  | Not relevant, Customer provision
| Follow up on progress on site (2h/week) | 0 | 0 | 0 |  |  | Not relevant, Customer provision
| Collection of installation protocols filled out by manpower company | 0 | 0 | 0 |  |  | Not relevant, Customer provision
| Document controlling | 0 | 0 |  |  | 0
Order of lifting equipment and scaffolding Activity for instalation | Clarify type of cranes needed | 0 | 0 | 0
| Clarify type of scaffolding needed | 0 | 0 | 0
| Clarification of lifting plans | 0 | 0 | 0
| Submit orders | 0 | 0 | 0
| Document controlling | 0 | 0 |  |  | 0
IDB - BCU After design freeze | Clarification of signal list (to be filled out) | 0 | 0 |  | 0
| Clarification logics and LEDs (to be filled out) | 0 | 0 |  | 0
| Paramatrisation of DIGSI (to be filled out) | 0 | 0 |  | 0
| As built documentation | 0 | 0 |  | 0
Activities for fabrication | Execution of FAT Poland (BCU/functional test) | 0 | 0 |  | 0
Activity for SAT & commisionning | Execution of SAT UK site (assistance to the SIE AG comm engineer) Hours per Bay | 0 | 0 |  | 0
Activity for SAT & commisionning | Execution of SAT UK site (assistance to the SIE AG comm engineer) hours per SWG | 0 | 0 |  | 0
| Back office support for inst. | 8 | 192 | 192
Preparation of the switchgear for sail-away | Back office | 0 | 0 | 0
Filling of SF6 offshore, testing and final commissioning | Back office | 0 | 0 | 0
Totals: |  |  |  | 1294.4 | 1413.6 | 696
TPM: | Primary Parts - Basic design: | 66.4
| Primary Parts - Detailed design: | 178.4
| Primary Parts - Manufact. & FAT: | 64
| Primary Parts - Delivery: | 40
| Sec Parts - Detailed Design: | 20.8
| Sec Parts - Delivery: | 48
| Cables - Basic Design: | 20.8
| Cables - Detailed Design: | 120
| Cables - Delivery: | 8
| I&C - Installation: | 272
| I&C - SAT: | 264
| I&C - Back office support: | 192
Sec. Eng: | Sec Parts - Basic design: | 605.6
| Sec Parts - Detailed Design: | 456
| Sec Parts - FAT | 256
| Sec Parts - As Built | 96
Doc. Controller: | Primary Parts - Basic design: | 32
| Primary Parts - Detailed design: | 140
| Sec Parts - Detailed Design: | 384
| Cables - Basic Design: | 4
| Cables - Detailed Design: | 32
| I&C - Installation: | 72
| I&C - SAT: | 32